## Slide 1: KiCK OFF_0 (IOT_Security)
Submitted to:
Dr. Hassan Mostafa

## Slide 2: Agenda
Draft Plan for thesis research and Milestones
Papers Skimmed So Far and there findings (8,9,13,17,18,19,and 99)
Next Steps

## Slide 3: Draft Plan for thesis research and Milestones
Feb.17 | March | April | May | June | July | Augu. | Sept. | Octob | Nove | Dece. | Jan 18
Papers Survey (28)
Short list 10
Short list 5
Main Point
BrainStorm
MS1: Simulation
Matlab
Matlab
Matlab
MS2:RTL & FPGA
FPGA
FPGA
FPGA
FPGA
MS3: ASIC (Std_cells)
ASIC
ASIC
MS4: Documentation&
Paper Submission

## Slide 4: Git and GitHub for CM and Backup
GitHub Project and GitHub desktop to be used for Project Configuration Management.
https://github.com/IslamHelmy/MasterThesis

## Slide 5: Papers Skimmed So Far and there findings (8,13)
Main Aspects of Secutiry:
  Authentication (Man in the Middle attack)
  Data Integrity (too short passwords) , i.e protection is low.
  Privacy of user Data
  Digital Forgetting
Security Protection mechanisms:
  Trust & reputation Mechanism
  Comm security such as end2end encryption
  Privacy of comm and user data
  Securing services and apps

## Slide 6: Papers Skimmed So Far and there findings (8,13)
Service-oriented architecture for IoT
Architecture for the Social IoT

## Slide 7: Papers Skimmed So Far and there findings (9)
Security Schemes
Blocktag
(unauth. Tracing)
Data Exchange
TEA
AES
@ RFID
ECC
@ WSN
Technically, the following issues should be addressed:
(1) the definition of security and privacy from the social, legal and cultural perspectives;
(2) the trust mechanism
(3) The communication security
(4) the privacy of communication and user data; and
(5) security of services and applications.
Notes: The applications of IoT might be affected by pervasive threats such as RFID tags attacks and data leakage.
In RFID systems, a number of security schemes and authentication protocols have been proposed to cope with security threats.
low-cost symmetric-key cryptography algorithms, such as:
  Advance Encryption Standard (AES),
  Tiny Encryption Algorithm (TEA)
  Elliptic curve cryptography (ECC)
The adaption of the existing Internet standards for interoperable protocols;
the security assurance for compassable services. The challenges in security and privacy protection are summarized as resilience to attacks,
data authentication, access control, and client privacy.

## Slide 8: Papers Skimmed So Far and there findings (99,19)
Providing End2End Security with LowPower within Lossy NW (Protocols such as ROLL aim to secure lower layers from the described attacks while conserving resources).
There are more than one security level:
  Security for Phy,Mac Layer communication
  Security for NW Layer
  Routing security
  Application Layer security
Notes: Routing Over Low power and Lossy networks

## Slide 9: Papers Skimmed So Far and there findings (17)
Notes: Main Security Attacks:
  Gathering
  Blocking
  Privacy Attack
  Imitation
Security Componenets:
  System Security (overall Framework)
  Network Security (Sensing,RFID, and WSNs)
  Application Security (IOT Apps)

## Slide 10: Papers Skimmed So Far and there findings (18)
The structure of IoT is generally divided into three layers
Perception Layer Sec. Problems
  Node Capture
  Fake Node
  DOS Attack
  Timing attach
  Routing threats
Network Layer Sec. Problems
  illegal access
  networks, eavesdropping information, confidentiality
  damage, integrity damage, DoS attack, Man-in-the middle
  attack, virus invasion, exploit attacks
Application Layer Sec. Problems

## Slide 11: Next Steps
Future Skimming of Papers (20,22,23,24,25,26,27,28)
Identify the 5 Main Papers needed for the research.
Anything else Suggested by Dr.
  1
  2
  3

## Slide 12: Papers List for referencing

## Slide 13
Thank You , Any Questions ?